## Ark1
Lofthus frukt og saft |  | Team: |  | Tor-Eric, Silje, Mattis, Lars, Julie |  |  |  | Start date: 01.02.2020 |  | End date: 15.03.2020
Task |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7
Date | Assigned to | time axis 2020-02-01 to 2020-03-15
Planning | bar: 2020-02-01 to 2020-02-09
Client meeting | Project manager | bar: 2020-02-01
Market research | Market research team | bar: 2020-02-02 to 2020-02-04
Content planning | Designer | bar: 2020-02-04 to 2020-02-06
Sitemap | Back-end developer | bar: 2020-02-06; 2020-02-08 to 2020-02-09
Design | bar: 2020-02-08 to 2020-02-20
Design plan meeting | Project manager | bar: 2020-02-08
Style tiles | Front-end developer | bar: 2020-02-09 to 2020-02-13
Visual design concepts | Front-end developer | bar: 2020-02-12 to 2020-02-13; 2020-02-15 to 2020-02-20
Build | bar: 2020-02-19 to 2020-03-05
Client approval meeting | Project manager | bar: 2020-02-19
HTML & CSS | Front-end developer | bar: 2020-02-20; 2020-02-22 to 2020-02-26
Javascript | Front-end developer | bar: 2020-02-25 to 2020-02-27; 2020-02-29 to 2020-03-02
Finising the site | Project manager, front-end developer, back-end developer, designer | bar: 2020-03-03 to 2020-03-05
Launch | bar: 2020-03-05 to 2020-03-13
Launch meeting | Project manager | bar: 2020-03-05
Cross platform testing | Front-end developer | bar: 2020-03-06 to 2020-03-07
UX/UI testing | Front-end developer | bar: 2020-03-08 to 2020-03-09
Refinement | Project manager, front-end developer, back-end developer, designer | bar: 2020-03-10
Bug fixes | Back-end developer | bar: 2020-03-11 to 2020-03-12
Launch | Project manager, front-end developer, back-end developer, designer | bar: 2020-03-14